## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/2-9/8 | - Had first meeting. Decided on project - Finished SPP. - got git setup - getting Jira setup, with several members learning Jira - at least one member familiarizing self with Django - Experimenting with AI tools | Members familiarizing self with Jira, Django, React Some issues setting up Git, Jira accounts | N/A | People are trying different git methods reaching out to professors familiarzing self with React/Django/Jira Planning a Jira meeting on Thursday | 0 | 0 | 0 | 0 | 0 | 24.5 | 20.5 | 5 | 5.5 | 2 | 0 | 0 | 0 | 7.5 | 3.5
1 | 9/9-9/21 | -Finished SDD -Getting Started on STD -Getting initial Frontend and backend setup -Have users be able to create accounts and login -Getting application hosted | Getting Docker/backend/frontend setup, or deployment not working Donjay getting aspects hosted | Some scheduling issues | Working together to solve initial front/backend setup, using different services for hosting, Finding odd times to meet | 2 | 15 | 54 | 4 | 54 | 72 | 61 | 12 | 15 | 6.5 | 1 | 13 | 4 | 3.5 | 16
2 | 9/22-10/6 | Front End: - Getting Banner up - Getting Friends page up: send, receive, accept/decline friend request, remove friends - Getting Planning page up: Create, delete, edit plans Backend: -Getting API for creating/editing/retrieving plans working -Getting API for sending/deleting friend requests, accepting/declining friend requests, removing friends Creating more tests, adding to STD, updating SPPP | Getting ID's from API to match up as desired, David had some issues with pytest. Something wrong with the frontend of the hosting environment need to connect certain things together in the backend for querying | David moved, as announced early on, but I should have made sure someone else was an interim team leader. The others ended up working well, and I picked it back up near the end | Trying to debug the server host to make sure they function properly for online. Seems to be a CORS error. Make new models in django for better querying | 5 | 5 | 2 | 2 | 48 | 69.75 | 62 | 8.75 | 8.5 | 1 | 0 | 35.5 | 12 | 3.5 | 2
3 | 10/7-10/13 | Front End: Editing Banner for better mobile views Adding Bios and making it so you can reach other user's bios Adding user profiles and that you can edit yours Adding more MUI Backend: API Dismiss, Undismiss, List Plans Getting API for user profiles setup Fixing RSVP interactions User profile edit functionalities Creating more tests, adding to STD, updating SPPP | Not able to extend the existing Django user class to include more fields. Issue with the production server with the backend api requests timing out and the frontend routing issues Issue with getting pytest early | Ashley less available last weekend, which was planned early | We planned around Ashley not being here, so we finished everything she needed to do before she left Someone else tested pytest Haolin was able to create a new model for user profiles due to issues with the base user Donjay was able to fix the the production server | 8 | 1 | 5 | 8 | 26 | 43.5 | 39.5 | 4.5 | 0 | 1 | 0 | 22.5 | 8 | 2.5 | 5

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
David Metraux | Management Plan | Added User Stories and Acceptance Tests for User Pages. Moved stuff from different sections as necesarry. | Most of the architecture section | Added manual tests for friends, user bios, and user profiles | Iteration 0 Presentation Iteration 3 Demo | 1. Banner/Logo 2. Front End Friends Page and Relevant logic 3. Front End User Bio/Profile 4. Front End Profile Editing https://github.com/BUMETCS673/cs673olf25project-cs673olf25_team3/issues?q=is%3Apr%20author%3Adavidmetraux | Added manual tests for friends, user bios, and user profiles Added https://github.com/BUMETCS673/cs673olf25project-cs673olf25_team3/blob/development/frontend/__tests__/Banner.test.tsx Edited tests for https://github.com/BUMETCS673/cs673olf25project-cs673olf25_team3/blob/development/frontend/__tests__/PlansCard.test.tsx | Got initial git setup | Getting documents in team folder, getting them setup for use. Making sure everyone did their required parts, like the individual progress reports Watching lectures so people know what we need to do Updating RiskAssesstment Summarizing Progress Reports Managing timeline to fit properly. Making sure work is properly submitted
Ashley Sachdeva | Proposed High Level requirements | Added User Stories and Acceptance Tests for Plans Pages. Added RSVPs/ delete/ dismiss user and acceptance tests. | UI design | Manual test cases for plans, rsvps and dismiss, automated tests for frontend | Iteration 2 Presentation | https://github.com/BUMETCS673/cs673olf25project-cs673olf25_team3/issues?q=is%3Apr%20author%3Aasach888 | Added unit tests within PRs and added manual test cases for frontend in STD. | Updated docker to be able to run our tests files | Staying ontop of backend contracts, splitting up requirements between team. Making sure things were tested and approved properly
Haolin Yang | Researched related works | Added user stories and acceptance tests for plan related functions. Opened several tickets on Jira to track my own progress. | Introduction and class diagram | Manual tests for backend RSVP and User functions | Iteration 1 Presentation | https://github.com/BUMETCS673/cs673olf25project-cs673olf25_team3/issues?q=is%3Apr%20author%3Ahaoliny-ops | Added unit tests and manual test cases for backend User and RSVP functionalities https://github.com/BUMETCS673/cs673olf25project-cs673olf25_team3/blob/development/backend/api/tests/rsvp_test.py https://github.com/BUMETCS673/cs673olf25project-cs673olf25_team3/blob/development/backend/api/tests/test_users.py |  | Watching for problems and feedbacks, trying to make sure my tasks are done in a timely manner, and communicating design decisions.
Donjay Barit | Configuration Management | Setup the Jira workflow for both kanban and sprint boards Opened task and bug tickets to track my own progress. Created Jira releases for iteration 1 and 2 Tried to update Jira ticket statuses in real time | Database design and security design | Manual tests for backend Plans API functions | Iteration 1 Presentation | https://github.com/BUMETCS673/cs673olf25project-cs673olf25_team3/issues?q=is%3Apr%20author%3Adonj808 | Added unit tests for Plans api https://github.com/BUMETCS673/cs673olf25project-cs673olf25_team3/blob/development/backend/api/tests/plans_test.py | Setup base source codes for frontend and backend. Setup docker files for frontend and backend Configured CI/CD pipeline and deployments Configured and setup live servers | Keeping team updated on progress of project's configurations especially with deployments, providing feedbacks to issues and code problems. Updating Jira project board statuses.
Jason Lee | Quality Assurance Plan | Added User Stories and Acceptance Tests for Friend. Updated my ticket progresses, and commmented notes on my tasks after PRs | Design Patterns and Architecture Diagram | Testing Summary, added part manual tests and testing metrics | Iteration 2 Presentation | https://github.com/BUMETCS673/cs673olf25project-cs673olf25_team3/issues?q=is%3Apr%20author%3Ajson-leef | Added unit & manual test cases for backend for friend connection, plans dismissal, jwt init setup https://github.com/BUMETCS673/cs673olf25project-cs673olf25_team3/blob/development/backend/api/tests/test_friends.py https://github.com/BUMETCS673/cs673olf25project-cs673olf25_team3/blob/development/backend/api/tests/test_plans_dismissal.py https://github.com/BUMETCS673/cs673olf25project-cs673olf25_team3/pull/16 | n/a | Providing updates on my tasks and addressing feedback or issues

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Ashley Sachdeva
Your Lead Roles: Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/2-9/8 | 3 | 2 | 1 | 1 - define high level requirements, overview, readme and about description in github. 2- review mocks for homepage 5- communicate with team on project setup, jira, github readme and requirements 6- add to the github with descriptions | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Use chatgpt for naming of project and help re-writing requirements in a clean format | 1. Write README, about/description for github project 2. Setup overview paragraph for project in SPPP and Write requirement list in SPPP | None | None | Help build out requirements, intialize frontend structure | 5
2 | 9/8-9/12 | 4 | 3 | 1 | 1- Hash out feature and requirements we need for application. 2- designed theme for Login and Signup page without connecting to the backend. 3- implemented skeleton of login/signup | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | AI tools for helping with formatting the CSS | No project iteration due this week. Added some code to the repository. | None
3 | 9/12-9/21 | 5 | 4 | 1 | 0- learned about refresh tokens. -3 implemented login/signup/auth refresh/ home page/ logout functionality. all wired up with the backend. 4- manually tested flows and added steps | 1 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | AI tools for helping with understanding refresh tokens: https://chatgpt.com/share/68d09dec-c340-8006-9a7c-f01fc142297b | Wrote design paragraph for SDD. Implemented features and connected with backend. Added manual testing steps to STD | None
4 | 9/21-9/28 | 5 | 4 | 1 | 4- added automated test setup for frontend and created tests for certain workflows. 5- requirements for future work | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | No AI tools for testing | No project iteration due this week. Added some code to the repository for test coverage | None | None | continue to build implementation | 8
5 | 9/28-10/5 | 9 | 8 | 1 | 1- requirements for implmentation work. 3- implemented add, edit, delete plans 4- added automated cases to code and manual test cases to STD 5- communicated with backend on requirements for contract | 0 | 1 | 0 | 5 | 1 | 1 | 0 | 0 | AI tools to help write certain parts of the error handling for API requests and component response | Contributed to a large feature of the iteration; adding, edtiting, deleting plans. Expanded automated and manual tests, updated the STD. | None | None | wrap up implementation, test, find edge cases and code smells
6 | 10/5-10/12 | 6 | 5 | 1 | 1- assessing final requirements. 3- implemented RSVPs, plans filtering and dismissing plans | 0 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | AI tools to help write certain parts of the error handling for API requests and component response | Contributed to a large feature of the iteration; rsvping, plans filtering and dismiss plan functionality | None | None | None

## Jason Lee
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/02-09/08 | 3 | 2 | 1 | 0 - Learning what goes into QA, standard practices 1 - Fill out QA section of SPPP 6 - Github Intros Lab1 | 1 | 1 | [6 empty] | Used chatGPT a bit in my research for what processes, standard practices, etc looks like in QA within a team | 1 - Write QA section on SPPP | 1 - Not super familiar with frameworks (Django & React) | 1 - Familiarize myself with frameworks, identify where I can help on project | 1 - Donjay will lead a meeting to walk-through Jira 2 - Familiarize myself with frameworks 3 - Start coding tasks | 6
2 | 9/9 -9/15 | 6 | 4 | 2 | 0 - Learning about JWT authentication 3 - Setup User Login with JWT Auth | 2 |  |  | 2 |  |  |  |  | Used chatGPT to help with learning of JWT | PJ-33 code push | An issue on my machine with MongoDB and Atlas Cloud. Wasn't able to get Docker working. | Solution found | One of the backend open tasks | 6
3 | 9/16-9/22 | 5.5 | 4.5 | 1 | 0 - Learn MongoDB, APIs, collections for PJ-14 1- Fill out Design Patterns & Rest APIs section on SDD 3 - Starting to work on PJ-14-Backend API for friends | 2 | 1.5 |  | 1 |  |  |  |  | ChatGPT to help with some learning, and with templates on how to fill out SDD sections | Design patterns & Rest API sections on SDD | None | None | Finish PJ-14 Work on new task and Iteration 2 | 7
4 | 9/23 - 9/29 | 3 | 2 | 1 | 0 - Continued learning about Django models, DB contraints, local testing flows, data model and persistence | 2 | [7 empty] | Resource to help learn certain topics | Some code in PJ-14, not fully done yet | None | None | Finish Friend Requests and work on Iteration 2 Presentation | 7
5 | 9/30 - 10/06 | 9 | 8 | 1 | 4 - Fill out parts of STD and prepare for Iteration 2 3 - pushed version of PJ-14-Friends-Users 3 - Debug errors on Friend Requests and users |  |  |  | 6.5 | 1.5 |  |  |  | Helped with stuck errors and syntax and comments/documentation | Friend requests & Iteration 2 presentation | Errors when testing from Frontend. ID keys mismatching, api.md not accurate, request edge cases | Solutions found | Find more edge cases, wrap up implementation and tests, take on backlog task | 8
6 | 10/6 - 10/13 | 7 | 6 | 1 | 3 - PJ-48 Dismiss Plans Backend 4 - Testing PJ-48, PJ-94 and plans |  |  |  | 4 | 2 |  |  |  | chatGpt for debugging and helping to write documentation | Backend - Dismiss, Undismiss, List Plans | None | None | None

## David Metraux
Your Lead Roles: Project Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/2-9/8 | 7.5 | 6.5 | 1 | 0 - learn new git gui 5 - getting documents setup in team folder, started working on agenda, writing risk assessment, writing meeting minutes, doing presentation, writing management plan, getting people to do their required parts, summarizing progress 6 - getting git setup. Uploading stuff to git. | 0.5 |  |  |  |  | 5.5 | 0.5 |  | I used AI to reword a paragraph I felt was unclear in the management plan. It was helpful, and I edited the results slightly to be more clear. | 1. Risk Management part of SPPP, including sheets 2. Setup git with team.md 3. Created and participated in iteration 0 presentation 4. Summarizing Progress Report | Couldn't get git bash to work on PC. | Continue to practice with Jira | Continue to practice with Jira | 6
2 | 9/9 -9/15 | 7 | 6 | 1 | 0 - Learning Jira, Docker, refreshing self on React and Django 1 -User Stories for lab 3- getting front end setup for friends page 5- getting agenda setup, directing 6- Configuring Docker | 1 | 1 |  | 0.5 |  | 0.5 | 3 |  | Getting some basic AI components for React down. It is sort of helpful, not much more helpful than just googling it. | 1. Assisting others with details on what is needed for Iteration 1 2. Getting started on friends page | Needing to spend a lot of time configuring Docker on my PC, lots of old Docker stuff. | Eventually figuring it out | Getting friends page setup | 6
3 | 9/16-9/22 | 7 | 6 | 1 | 0 - learning Material UI, learning about vector graphics 3- Setting up banner, trying to setup friends page more 5- Getting agenda setup, verifying what needs to be done, making sure people are doing what needs to be done, summarizing progress 6 - getting backend setup | 1 |  |  | 2 |  | 2 | 1 |  | Using AI to research Architecture concepts | 1. Banner, logo for website 2. Architecture portion for SDD 3. Getting started on manual aspects of STD 4. Summarizing progress report 5. Submitting everything | Having problems setting up backend | Having teammates help out | Getting logout setup, setting up friends page | 7
4 | 9/23-9/29 | 2.75 | 2.5 | 0.25 | 3- Working on friends page 4- Adding tests 5- checking requirements, writing agenda |  |  |  | 1 | 1 | 0.5 |  |  | seeing some ways to setup test cases | 1. Adding tests 2. Organizing meeting/requirements | Getting connection with the backend | Meeting with Ashley for help | actually setting up the friends page | 7
5 | 9/30-10/06 | 10.5 | 10 | 0.5 | 0 - Remembering about use effect and similar hooks 3 - Getting friends page setup, setting up new banner 5 - Communicating aspects of how the front and back end connects, checking requirements, writing agenda | 0.5 |  |  | 9 |  | 0.5 |  |  | Used AI to help me program the buttons! It was useful | 1. Banner lets us change page 2. Friends page that lets us add friends | Can't get pytest to work in the same way others can | Work with teammates and use tutorials | Debugging, making UI look prettier | 10
6 | 10/7-10-13 | 12.5 | 12 | 0.5 | 3- Getting Bio pages working, having links to bio pages, getting profile page working, getting links to profile pages, getting editting profile page working properly, adjusting banner to fit profile and on smaller screens, adding mui to friends page 4- Fixing tests that didn't work, testing all implemented aspects manually 5 - Staying up late and assisting to get the iteration 2 in, writing agenda, telling people what we need to do for final iteration 7- working on presentation |  |  |  | 8 | 1 | 2 |  | 1 | Using AI to help me program links and the navigation, it was useful | 1. Getting User Bio Page setup 2. Getting User Profile Page setup 3. Getting form for editing profile page setup 4. Adding LInks to usernames to send to bio/profile 5. Adding Profile link to banner 6. Adjusting banner to fit better on mobile views 7. Adding MUI to pages | Couldn't get pytest to work | Have someone else verify pytest things

## Donjay Barit
Your Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/02-09/08 | 6 | 5 | 1 | 0 - learn Django structure 6 - Setup Jira kanban and scrum boards and development workflow, create hosting account on render.com, setup team gmail account to be used for vendor signups | 2 | [5 empty] | 3 |  |  | 1. Write configuration/management section of SPPP 2. added bio in git | 1. limited experience with Django framework 2. determine deployment processes for a backend and frontend branches in a monorepo | 1. familiarize myself with the Django framework structure 2. research and lookup examples of monorepos deployment processes | 1. setup the backend environment base structure including api and database 2. create docker containers for project 3. create task items in Jira 4. begin implementations of project codebase for iteration 1 5. lead a group meeting about Jira | 12
2 | 9/9-9/15 | 9 | 7 | 2 | 4 - Perfmored QA and fix conflicts on pull requests 6 - Setup the base frameworks for the backend and frontend, configure docker containers, setup the remote databases |  |  |  |  | 1 |  | 6 |  | ChatGPT to help fix issues with docker container issues, mostly with network setups and commands. | 1. Setup the codebase for the backend 2. Setup the codebase for the frontend 3. Created remote database accounts 4. Created docker containers for local developments | 1. There is an issue with connecting the local database with the backend when performing test scripts using the docker containers. Without docker it is working fine. | 1. Research how to properly set up docker networks between containers | Setup the CI/CD processes | 10
3 | 9/16-9/22 | 11 | 10 | 1 | 0 - learn Github Action CI/CD process, research hosting providers 4 - Perfmored QA on pull requests, update mongodb connection configs, added test library to frontend 6 - Finalize the CI/CD pipeline priocess, setup and test staging CI/CD, configure hosting services | 3 |  |  |  | 2 |  | 5 |  | ChatGPT to get advice on the process to deploy with Github Action pertaining to docker and hosting providers. It provided multiple options and still weighing best course to take that may involved a mixture of the options AI provided. | 1. Made improvement to setting database environment variables. 2. Added test library to react app 3. Setup staging and production servers on new hosting provider | 1. Deploying to the hosting provider Render, created memory issues with the limitation of the free tier. | 1. Resolved by moving to a new hosting provider DigitalOcean with more CPU, memory and storage. | 1. Configure security setup for the new hosting provider. 2. Configure production CI/CD 3 Assist with backend or frontend codes | 15
4 | 9/23-9/29 | 9 | 8 | 1 | 3 - Plans API CRUD implementations 4 - Test plans database creation logic 6 - Setup production servers 7 - Close Jira sprint 1 and start sprint 2, create Jira release for sprint 1, create API documentation |  |  |  | 4 | 1 |  | 2 | 1 | ChatGPT to help with the API and testing for the Plans CRUD methods. Helped to resolve errors in the production codes | 1. Implemented the Plans API CRUD methods and created test script to test plans creation | 1. Frontend production build has an issue with the environment variables creating issues communicating with the backend url. | 1. Modify the prodcution Dockerfile for the frontend to incorporate environment variables | 1. Improving the API structure with refactors 2. fix the production build for the frontend 3. Research media file storage | 10
5 | 9/30-10/06 | 10 | 9 | 1 | 3 - Plans API 4 - Review and test pull requests |  |  |  | 7 | 2 |  |  |  |  | 1. Filtering plans data by dates and users | 1. Issue with the querying friends to attach to plans query lists | 1. Look into the friends model and figure out how to connect or join the database with the plans data | 1. Continue with the plans api and clean up code 2. Write up test scripts for plan API 3. Secure and update servers | 10
6 | 10/07-10/13 | 10 | 9 | 1 | 3 - Plans API and tests, ensure json responses across all backend endpoints 4 - Review, test and merge pull requests 6 - Debug staging and production server issues 7 - Update Jira board statuses, updated the database design in SDD |  |  |  | 2 | 2 |  | 5 | 1 | ChatGPT to help with debugging server issues | 1. Updated plans api and fix edge cases | 1. Issue with the production server with the backend api requests timing out and the frontend routing issues | 1. Staging servers CORS issue has been resolved. 2. Production server required reconfigurations of docker and nginx files and reseting database credentials.

## Haolin Yang
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/2-9/8 | 5 | 5 | 1 | 0 - learning Jira 0 - learning Github 5 - Communicate with the team for ideas 7 - Researching what other softwares and platforms have similar features | 2 |  |  |  |  | 1 |  | 2 | ChatGPT to help research related applications | Researched related works section in the SPPP document | Have trouble connecting Jira to my github, saying that it can only be done by an organization owner | Find another way of code review or contact professor about this | - Using Jira - Set up development environment - Coding | 8
2 | 9/9-9/15 | 8 | 8 | 1 | 0 - learning Django 1 - Analyzing feature requirements 3 - Writing code 5 - Team meetings 6 - Set up environments | 3 | 1 |  | 2.5 |  | 1 | 0.5 |  | Cursor to help with coding AI notetaker to take meeting notes | Added basic user registration related functionalities and development QoL file to the code. | None |  | - Coding - SDD document | 8
3 | 9/16-9/22 | 9.5 | 8.5 | 1 | 0 - Learning Django 1 - Analyzing features 3 - Writing code 6 - Fixing working environment 7 - Working on SDD 7 - Working on presentation | 2 | 2 |  | 1 |  |  | 0.5 | 4 | ChatGPT to finalize class diagram and add additional features Cursor to help with coding | Introduction and class diagram of the SDD document Backend log out function (WIP) | Errors during deployment and testing | Fixed, resulted from a change in database configuration that I was not aware of. | - Coding - Testing - Lab - STD document | 7
4 | 9/23-9/30 | 4.5 | 4 | 1 | 0 - Learning Django 0 - Learning Pytest 4 - Testing 5 - Team meetings | 4 |  |  |  |  | 0.5 | [6 empty] | - Coding - Testing | 6
5 | 10/1-10/7 | 7 | 6.5 | 1 | 0 - Learning Django 0 - Learning Pytest 3 - Coding 4 - Testing | 2 |  |  | 3 | 2.5 |  |  |  | Cursor to help with coding | RSVP functions - CRD |  |  | - Coding | 7
6 | 10/8-10/14 | 8 | 7.5 | 1 | 3 - Coding 4 - Testing 5 - Team meeting |  |  |  | 4.5 | 3 | 0.5 |  |  | Cursor to help with coding | Fixed RSVP interactions User profile edit functionalities User related tests | Not able to extend the existing Django user class to include more fields | Fixed using a separate class acting as the user profile that is linked to the user class