## Sheet1
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 32 | team leader and all members | 2025-10-14 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | Add more team memeber | 1 | 3 | 2 | 30 | team leader and all members | 2025-10-14 | Divvy up tasks to new member, onboard them | Nobody has been added so far | Open
| Lack of motivation or responsibility | When team members do not do their respective work | 3 | 3 | 3 | 27 | requirement leader/team leader | 2025-10-14 | Remind someone what needs to be done of them, see if there are others that can do the work | Everyone is doing their jobs so far | Open
| Less availability | A team member is not very available for a week | 3 | 3 | 3 | 27 | team leader and all members |  | Hopefully tell a week in advance, where team members can then split up share of duties. If is sudden treat as a loss of a team member | David has moved and we are past that. Ashley is going to be doing a marthon during the last weekend, so we are preparing for that. | Open
Communication | duplicate work | When multiple team members are doing the same thing | 3 | 2 | 1 | 12 | team leader and all members | 2025-10-14 | Discuss which parts we will use, see if we can combine, or have one person take over. | No issues | Open
| worked on wrong components | When team members are working on the wrong thing | 3 | 3 | 3 | 27 | team leader and all members | 2025-10-14 | Re-define who needs to do what. See if the wrong component can still be used | No issues | Open
| useless work | When team members are working on something that doesn't help | 2 | 4 | 4 | 32 | requirement leader/team leader | 2025-10-14 | Discuss with team member what they could be doing instead. | No issues | Open
| inconsistent work | When team members are not achieving their goals well | 2 | 3 | 4 | 48 | requirement leader | 2025-10-14 | Point out what the engineer can be doing better. Potentially point to a tutorial or something. | No issues | Open
Requirements | unclear requirements | When it is unclear what is required to finish the project | 3 | 3 | 3 | 27 | requirement leader, other team members | 2025-10-14 | Have the requirement leader clarify what should be done. | No issues | Open
| scope creep | When new requirements get added and it is making the project too complex | 4 | 2 | 2 | 16 | requirement leader, other team members | 2025-10-14 | Redefine what is actually important to finish the project. | No issues | Open
| constant requirements changes | When requirements change and it gets confusing. | 2 | 2 | 1 | 16 | team leader, other members | 2025-10-14 | Have a meeting to to note which aspects should stay consistent. | No issues | Open
Management | improper task assignments | When task assignments are not properly done. | 4 | 3 | 4 | 24 | team members besides the leader | 2025-10-14 | discuss with team leader that there should be a change to how tasks are assigned, feedback | No issues | Open
| improper planning | When plans are not very well thought out | 4 | 3 | 4 | 24 | team members besides the leader | 2025-10-14 | Discuss with team leader a better idea for plan | No issues | Open
| lack of management skills | When the team leader is not very good at managing | 5 | 2 | 4 | 16 | team leader, other members | 2025-10-14 | Consider changing the team leader, work with others to see their thoughts | We had to rush during the end of iteration 1 | Open
Technology competence | Not familiar with the framework used | When a team member is not familiar with the framework | 4 | 3 | 3 | 18 | team leader, design and implementation, configuration | 2025-10-14 | Either reassign task or direct to tutorial | Ashley met with David to explain steps to make the front end better | Open
| Not familiar with the programming language used | When a team member is not familiar with the programming language | 2 | 3 | 4 | 48 | team leader, design and implementation, configuration | 2025-10-14 | Either reassign task or direct to tutorial | No issues | Open
| Not familiar with unit testing | When a team member is not familiar with unit testing | 2 | 2 | 2 | 32 | QA leader | 2025-10-14 | Either reassign task or direct to tutorial | No issues | Open
| Other technology incompetence | When a team member is not familiar with the technology | 2 | 3 | 3 | 36 | team leader, design and implementation, configuration | 2025-10-14 | Either reassign task or direct to tutorial | No issues | Open
| Not familiar with Git | When a team member is not familiar with git | 1 | 4 | 2 | 20 |  | 2025-10-14 | direct to tutorial, potentially meet | No issues | Open
Design and implementation | Improper design | When the design of the project has issues | 2 | 3 | 3 | 36 | design and implementation | 2025-10-14 | call a meeting to discuss changes | No issues | Open
| improper technology stack | When the tecnology stack is not a good fit for the project | 2 | 4 | 4 | 32 | design and implementation | 2025-10-14 | Call a meeting to discuss changes, provide potential alternatives | No issues | Open
| Messy code | When the code is hard to work with. | 3 | 3 | 3 | 27 | design and implementation | 2025-10-14 | Work with whoever is writing messy code to make it less messy | No issues | Open
Testing | Not enough testing | When there is not enough testing to keep functions properly functioning | 3 | 3 | 2 | 18 | qa leader | 2025-10-14 | Make more tests | No issues | Open
Integration and deployment | Not enough time for integration and deployment | When there is not enough time to finish the project. | 2 | 4 | 3 | 24 | design and implementation, everyone | 2025-10-14 | Meeting to cut losses, redefine end goals | No issues | Open
| Servers are down | When servers are down and that makes it hard to test the system | 2 | 3 | 3 | 36 | everyone, configuration leader | 2025-10-14 | If it is a temporary outage, is not that bad, and hopefully we can all work on something else. If it is long term or repeated, we will have to see about getting a new service provider | No issues | Open