## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/2-9/8 | - Had first meeting. Decided on project - Finished SPP. - got git setup - getting Jira setup, with several members learning Jira - at least one member familiarizing self with Django - Experimenting with AI tools | Members familiarizing self with Jira, Django, React Some issues setting up Git, Jira accounts | N/A | People are trying different git methods reaching out to professors familiarzing self with React/Django/Jira Planning a Jira meeting on Thursday | 0 | 0 | 0 | 0 | 0 | 24.5 | 20.5 | 5 | 5.5 | 2 | 0 | 0 | 0 | 7.5 | 3.5
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
David Metraux | Management Plan |  |  |  | Iteration 0 Presentation |  |  | Got git setup | Getting documents in team folder, getting them setup for use. Making sure everyone did their required parts, like the individual progress reports

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Ashley Sachdeva
Your Lead Roles: Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/2-9/8 | 3 | 2 | 1 | 1 - define high level requirements, overview, readme and about description in github. 2- review mocks for homepage 5- communicate with team on project setup, jira, github readme and requirements 6- add to the github with descriptions | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Use chatgpt for naming of project and help re-writing requirements in a clean format | 1. Write README, about/description for github project 2. Setup overview paragraph for project in SPPP and Write requirement list in SPPP | None | None | Help build out requirements, intialize frontend structure | 5

## Donjay Barit
Your Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
| 09/02-09/08 | 6 | 5 | 1 | 0 - learn Django structure 6 - Setup Jira kanban and scrum boards and development workflow, create hosting account on render.com, setup team gmail account to be used for vendor signups | 2 | [5 empty] | 3 |  |  | 1. Write configuration/management section of SPPP 2. added bio in git | 1. limited experience with Django framework 2. determine deployment processes for a backend and frontend branches in a monorepo | 1. familiarize myself with the Django framework structure 2. research and lookup examples of monorepos deployment processes | 1. setup the backend environment base structure including api and database 2. create docker containers for project 3. create task items in Jira 4. begin implementations of project codebase for iteration 1 5. lead a group meeting about Jira | 12

## Jason Lee
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/02-09/08 | 3 | 2 | 1 | 0 - Learning what goes into QA, standard practices 1 - Fill out QA section of SPPP 6 - Github Intros Lab1 | 1 | 1 | [6 empty] | Used chatGPT a bit in my research for what processes, standard practices, etc looks like in QA within a team | 1 - Write QA section on SPPP | 1 - Not super familiar with frameworks (Django & React) | 1 - Familiarize myself with frameworks, identify where I can help on project | 1 - Donjay will lead a meeting to walk-through Jira 2 - Familiarize myself with frameworks 3 - Start coding tasks | 6

## David Metraux
Your Lead Roles: Project Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/2-9/8 | 7.5 | 6.5 | 1 | 0 - learn new git gui 5 - getting documents setup in team folder, started working on agenda, writing risk assessment, writing meeting minutes, doing presentation, writing management plan, getting people to do their required parts, summarizing progress 6 - getting git setup. Uploading stuff to git. | 0.5 |  |  |  |  | 5.5 | 0.5 |  | I used AI to reword a paragraph I felt was unclear in the management plan. It was helpful, and I edited the results slightly to be more clear. | 1. Risk Management part of SPPP, including sheets 2. Setup git with team.md 3. Created and participated in iteration 0 presentation 4. Summarizing Progress Report | Couldn't get git bash to work on PC. | Continue to practice with Jira | Continue to practice with Jira | 6

## Haolin Yang
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/2-9/8 | 5 | 5 | 1 | 0 - learning Jira 0 - learning Github 5 - Communicate with the team for ideas 7 - Researching what other softwares and platforms have similar features | 2 |  |  |  |  | 1 |  | 2 | ChatGPT to help research related applications | Researched related works section in the SPPP document | Have trouble connecting Jira to my github, saying that it can only be done by an organization owner | Find another way of code review or contact professor about this | - Using Jira - Set up development environment - Coding | 8