## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/2-9/8 | - Had first meeting. Decided on project - Finished SPP. - got git setup - getting Jira setup, with several members learning Jira - at least one member familiarizing self with Django - Experimenting with AI tools | Members familiarizing self with Jira, Django, React Some issues setting up Git, Jira accounts | N/A | People are trying different git methods reaching out to professors familiarzing self with React/Django/Jira Planning a Jira meeting on Thursday | 0 | 0 | 0 | 0 | 0 | 24.5 | 20.5 | 5 | 5.5 | 2 | 0 | 0 | 0 | 7.5 | 3.5
1 | 9/9-9/21 | -Finished SDD -Getting Started on STD -Getting initial Frontend and backend setup -Have users be able to create accounts and login -Getting application hosted | Getting Docker/backend/frontend setup, or deployment not working Donjay getting aspects hosted | Some scheduling issues | Working together to solve initial front/backend setup, using different services for hosting, Finding odd times to meet | 2 | 15 | 54 | 4 | 54 | 72 | 61 | 12 | 15 | 6.5 | 1 | 10 | 4 | 3.5 | 19
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
David Metraux | Management Plan |  |  |  | Iteration 0 Presentation |  |  | Got git setup | Getting documents in team folder, getting them setup for use. Making sure everyone did their required parts, like the individual progress reports

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Ashley Sachdeva
Your Lead Roles: Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/2-9/8 | 3 | 2 | 1 | 1 - define high level requirements, overview, readme and about description in github. 2- review mocks for homepage 5- communicate with team on project setup, jira, github readme and requirements 6- add to the github with descriptions | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Use chatgpt for naming of project and help re-writing requirements in a clean format | 1. Write README, about/description for github project 2. Setup overview paragraph for project in SPPP and Write requirement list in SPPP | None | None | Help build out requirements, intialize frontend structure | 5
2 | 9/8-9/12 | 4 | 3 | 1 | 1- Hash out feature and requirements we need for application. 2- designed theme for Login and Signup page without connecting to the backend. 3- implemented skeleton of login/signup | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | AI tools for helping with formatting the CSS | No project iteration due this week. Added some code to the repository. | None
3 | 9/12-9/21 | 5 | 4 | 1 | 0- learned about refresh tokens. -3 implemented login/signup/auth refresh/ home page/ logout functionality. all wired up with the backend. 4- manually tested flows and added steps | 1 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | AI tools for helping with understanding refresh tokens: https://chatgpt.com/share/68d09dec-c340-8006-9a7c-f01fc142297b | Wrote design paragraph for SDD. Implemented features and connected with backend. Added manual testing steps to STD | None

## Donjay Barit
Your Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
| 09/02-09/08 | 6 | 5 | 1 | 0 - learn Django structure 6 - Setup Jira kanban and scrum boards and development workflow, create hosting account on render.com, setup team gmail account to be used for vendor signups | 2 | [5 empty] | 3 |  |  | 1. Write configuration/management section of SPPP 2. added bio in git | 1. limited experience with Django framework 2. determine deployment processes for a backend and frontend branches in a monorepo | 1. familiarize myself with the Django framework structure 2. research and lookup examples of monorepos deployment processes | 1. setup the backend environment base structure including api and database 2. create docker containers for project 3. create task items in Jira 4. begin implementations of project codebase for iteration 1 5. lead a group meeting about Jira | 12
| 9/9-9/15 | 9 | 7 | 2 | 4 - Perfmored QA and fix conflicts on pull requests 6 - Setup the base frameworks for the backend and frontend, configure docker containers, setup the remote databases |  |  |  |  | 1 |  | 6 |  | ChatGPT to help fix issues with docker container issues, mostly with network setups and commands. | 1. Setup the codebase for the backend 2. Setup the codebase for the frontend 3. Created remote database accounts 4. Created docker containers for local developments | 1. There is an issue with connecting the local database with the backend when performing test scripts using the docker containers. Without docker it is working fine. | 1. Research how to properly set up docker networks between containers | Setup the CI/CD processes | 10
| 9/16-9/22 | 11 | 10 | 1 | 0 - learn Github Action CI/CD process, research hosting providers 4 - Perfmored QA on pull requests, update mongodb connection configs, added test library to frontend 6 - Finalize the CI/CD pipeline priocess, setup and test staging CI/CD, configure hosting services | 3 |  |  |  | 2 |  | 5 |  | ChatGPT to get advice on the process to deploy with Github Action pertaining to docker and hosting providers. It provided multiple options and still weighing best course to take that may involved a mixture of the options AI provided. | 1. Made improvement to setting database environment variables. 2. Added test library to react app 3. Setup staging and production servers on new hosting provider | 1. Deploying to the hosting provider Render, created memory issues with the limitation of the free tier. | 1. Resolved by moving to a new hosting provider DigitalOcean with more CPU, memory and storage. | 1. Configure security setup for the new hosting provider. 2. Configure production CI/CD 3 Assist with backend or frontend codes | 18

## Jason Lee
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/02-09/08 | 3 | 2 | 1 | 0 - Learning what goes into QA, standard practices 1 - Fill out QA section of SPPP 6 - Github Intros Lab1 | 1 | 1 | [6 empty] | Used chatGPT a bit in my research for what processes, standard practices, etc looks like in QA within a team | 1 - Write QA section on SPPP | 1 - Not super familiar with frameworks (Django & React) | 1 - Familiarize myself with frameworks, identify where I can help on project | 1 - Donjay will lead a meeting to walk-through Jira 2 - Familiarize myself with frameworks 3 - Start coding tasks | 6
2 | 9/9 -9/15 | 6 | 4 | 2 | 0 - Learning about JWT authentication 6 - Setup User Login with JWT Auth | 2 | [5 empty] | 2 |  | Used chatGPT to help with learning of JWT | PJ-33 code push | An issue on my machine with MongoDB and Atlas Cloud. Wasn't able to get Docker working. | Solution found | One of the backend open tasks | 6
3 | 9/16-9/22 | 5.5 | 4.5 | 1 | 0 - Learn MongoDB, APIs, collections for PJ-14 1- Fill out Design Patterns & Rest APIs section on SDD 6 - Starting to work on PJ-14-Backend API for friends | 2 | 1.5 |  |  |  |  | 1 |  | ChatGPT to help with some learning, and with templates on how to fill out SDD sections | Design patterns & Rest API sections on SDD |  |  | Finish PJ-14 Work on new task and Iteration 2 | 7

## David Metraux
Your Lead Roles: Project Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/2-9/8 | 7.5 | 6.5 | 1 | 0 - learn new git gui 5 - getting documents setup in team folder, started working on agenda, writing risk assessment, writing meeting minutes, doing presentation, writing management plan, getting people to do their required parts, summarizing progress 6 - getting git setup. Uploading stuff to git. | 0.5 |  |  |  |  | 5.5 | 0.5 |  | I used AI to reword a paragraph I felt was unclear in the management plan. It was helpful, and I edited the results slightly to be more clear. | 1. Risk Management part of SPPP, including sheets 2. Setup git with team.md 3. Created and participated in iteration 0 presentation 4. Summarizing Progress Report | Couldn't get git bash to work on PC. | Continue to practice with Jira | Continue to practice with Jira | 6
2 | 9/9 -9/15 | 7 | 6 | 1 | 0 - Learning Jira, Docker, refreshing self on React and Django 1 -User Stories for lab 3- getting front end setup for friends page 5- getting agenda setup, directing 6- Configuring Docker | 1 | 1 |  | 0.5 |  | 0.5 | 3 |  | Getting some basic AI components for React down. It is sort of helpful, not much more helpful than just googling it. | 1. Assisting others with details on what is needed for Iteration 1 2. Getting started on friends page | Needing to spend a lot of time configuring Docker on my PC, lots of old Docker stuff. | Eventually figuring it out | Getting friends page setup | 6
3 | 9/16-9/22 | 7 | 6 | 1 | 0 - learning Material UI, learning about vector graphics 3- Setting up banner, trying to setup friends page more 5- Getting agenda setup, verifying what needs to be done, making sure people are doing what needs to be done, summarizing progress 6 - getting backend setup | 1 |  |  | 2 |  | 2 | 1 |  | Using AI to research Architecture concepts | 1. Banner, logo for website 2. Architecture portion for SDD 3. Getting started on manual aspects of STD 4. Summarizing progress report 5. Submitting everything | Having problems setting up backend | Having teammates help out | Getting logout setup, setting up friends page | 7

## Haolin Yang
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/2-9/8 | 5 | 5 | 1 | 0 - learning Jira 0 - learning Github 5 - Communicate with the team for ideas 7 - Researching what other softwares and platforms have similar features | 2 |  |  |  |  | 1 |  | 2 | ChatGPT to help research related applications | Researched related works section in the SPPP document | Have trouble connecting Jira to my github, saying that it can only be done by an organization owner | Find another way of code review or contact professor about this | - Using Jira - Set up development environment - Coding | 8
2 | 9/9-9/15 | 8 | 8 | 1 | 0 - learning Django 1 - Analyzing feature requirements 3 - Writing code 5 - Team meetings 6 - Set up environments | 3 | 1 |  | 2.5 |  | 1 | 0.5 |  | Cursor to help with coding AI notetaker to take meeting notes | Added basic user registration related functionalities and development QoL file to the code. | None |  | - Coding - SDD document | 8
2 | 9/16-9/22 | 9.5 | 8.5 | 1 | 0 - Learning Django 1 - Analyzing features 3 - Writing code 6 - Fixing working environment 7 - Working on SDD 7 - Working on presentation | 2 | 2 |  | 1 |  |  | 0.5 | 4 | ChatGPT to finalize class diagram and add additional features Cursor to help with coding | Introduction and class diagram of the SDD document Backend log out function (WIP) | Errors during deployment and testing | Fixed, resulted from a change in database configuration that I was not aware of. | - Coding - Testing - Lab - STD document | 7